## Risk Register
Monteverde Airport – Information Security Risk Register (RISK-REG-2026-001)
Method: NIST SP 800-30 Rev.1 / ISO/IEC 27005 (qualitative 5x5). Treatment per ISO/IEC 27001:2022. Date: 2026-10-10. Scores are reasoned estimates for the simulated airport scenario, not measured values.
Legend: blue cells (Likelihood, Impact, Treatment) are inputs — edit them; Score and Level are formulas and update automatically. Scales and level bands: see 'Scales' sheet.
ID | Asset / area | Threat | Vulnerability | Existing controls | Likelihood (1-5) | Impact (1-5) | Score (L×I) | Level | Treatment
R-01 | OPNsense firewall (management GUI) | Unauthorised access to firewall management from the check-in zone | Anti-lockout rule leaves the GUI reachable from the whole check-in LAN; Office/IT admin zone not yet built | Web rules exclude PRIVATE_NETS; GUI over HTTPS; SecOps admin restricted to soc-ws01 | 3 | 5 | 15 | High | Mitigate
R-02 | Wazuh manager (agent enrollment) | Rogue or spoofed agent registers with the SIEM | Agent enrollment has no password/authentication | Enrollment ports (1514/1515) reachable only from the two active zones | 2 | 4 | 8 | Medium | Mitigate
R-03 | checkin-srv / checkin-pc01 (file integrity) | Undetected tampering with critical files | FIM runs on a schedule, not in real time | Wazuh FIM active on a schedule; Sysmon on checkin-pc01 | 3 | 3 | 9 | Medium | Mitigate
R-04 | Internal time service (NTP) | Time spoofing that corrupts log correlation and certificate validation | Internal NTP (firewall → hosts) is not authenticated | Single internal time source (firewall); Hyper-V time sync disabled on guests | 2 | 3 | 6 | Medium | Accept
R-05 | Grafana (mon-srv) | Interception of monitoring credentials / data | Grafana served over plain HTTP | Reachable only from soc-ws01 (ufw + firewall rule) | 2 | 2 | 4 | Low | Mitigate
R-06 | mon-srv, soc-ws01, firewall (telemetry) | Attacker activity on hosts without a SIEM agent goes unseen | No Wazuh agent on mon-srv/soc-ws01; perimeter blocks visible only in OPNsense live view; soc-ws01 ufw blocks stay local | Host ufw active everywhere; perimeter firewall logging; Sysmon on the endpoint | 3 | 4 | 12 | High | Mitigate
R-07 | Network segmentation | Lateral movement / admin traffic outside a controlled zone | Office/IT zone not built; VM administration from the Hyper-V console on the host | Stateful firewall, default-deny between zones; only two zones active | 2 | 4 | 8 | Medium | Accept
R-08 | checkin-pc01 (Windows 11 evaluation) | Loss of the endpoint / lab environment | Evaluation licence expires ~end December 2026 | Checkpoints taken; chapter work completed before expiry | 4 | 2 | 8 | Medium | Accept
R-09 | Wazuh detection rules | Missed detection or alert fatigue | Custom rule 100101 (port scan) not fully tuned; MITRE tags incomplete on custom rules | Custom rules tested with wazuh-logtest; sysmon-modular ruleset | 3 | 3 | 9 | Medium | Mitigate
R-10 | Host firewall logging (ufw) | Security-relevant packets not recorded | ufw logging set to 'low' (samples packets, not all) | ufw active on servers and soc-ws01; blocks forwarded to Wazuh on checkin-srv | 3 | 2 | 6 | Medium | Accept
R-11 | checkin-pc01 (host configuration) | Residual weakening of endpoint hardening after lab exercises | PowerShell execution policy left at RemoteSigned (CurrentUser) after chapter 9 | Atomic Red Team removed via pre-atomic checkpoint; Defender stayed active throughout | 2 | 2 | 4 | Low | Accept
R-12 | Hyper-V host (VM management) | Slow or error-prone recovery actions under pressure | Hyper-V PowerShell module not installed on the host; management is GUI-only | Documented GUI procedures for checkpoint/network/restore | 2 | 2 | 4 | Low | Accept
R-13 | checkin-srv (business application) | The core business service cannot be protected or monitored in context | Check-in application not yet deployed on checkin-srv | Host hardened (ufw, static IP, NTP, Wazuh agent) ready to host it | 3 | 2 | 6 | Medium | Accept
Summary by level
| Critical | 0
| High | 2
| Medium | 8
| Low | 3
| Total risks | 13

## Scales
Scales and level bands
Likelihood |  | Impact
Score | Meaning | Score | Meaning
1 | Rare | 1 | Negligible
2 | Unlikely | 2 | Minor
3 | Possible | 3 | Moderate
4 | Likely | 4 | Major
5 | Almost certain | 5 | Severe (operations stopped / large data breach)
Level bands (lab convention — edit the lower bounds in blue to change thresholds)
Min score | Level
1 | Low
5 | Medium
10 | High
16 | Critical
Treatment options (ISO/IEC 27001:2022): Mitigate · Accept · Avoid · Transfer
Note on A14: Low starts at 1 (minimum possible score). Bands are a stated lab convention, not a standard.

## Treatment Plan
Risk treatment plan – actions for 'Mitigate' items
ID | Level | Planned action | Status
R-01 | High | Build the Office/IT zone and restrict firewall management to it; tighten the anti-lockout exposure | Planned
R-06 | High | Install Wazuh agents on mon-srv and soc-ws01; forward OPNsense logs (syslog) to Wazuh | Planned
R-02 | Medium | Enable Wazuh agent enrollment password | Planned
R-03 | Medium | Set FIM to realtime on critical directories | Planned
R-05 | Low | Issue a TLS certificate for Grafana | Planned
R-09 | Medium | Tune rule 100101; add MITRE technique tags to custom rules | Planned